## Sheet1
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2021
Province, City or Municipality: CALAUAN
Program or Project |  | Location | Total Cost | Date Started | Target | Project Status |  | No. of | Remarks
[5 empty] | Completion | % of | Total Cost | Extensions,
[5 empty] | Date | Completion | Incurred to Date | if any
SOCIAL DEVELOPMENT
1 | Construction of Evacuation Center | Brgy. Sto. Tomas | 1996466.01 | 2018-10-01 |  | 85 | 1696996.11 |  | On-Going | 299469.9
ECONOMIC DEVELOPMENT
3 | Repair of Concrete Bridge at Purok 1 | Brgy. Lamot 1 | 496870 | 2018-06-01 |  | 89.3542 | 443974.4 |  | On-Going | 52895.6
7 | Concreting of Pathway at Purok 3 & 4, Brgy. Imok | Brgy. Imok | 848192.46 | 2019-02-01 |  | 79.7567 | 676490.67 |  | On-Going | 171701.79
8 | Construction of Limao to Perez Road | Brgy. Limao to Perez Road | 25729326.57 | 2019-12-01 |  | 65.2827 | 16796799.35 |  | On-Going | 8932527.22
ENVIRONMENTAL MANAGEMENT
9 | Riprapping of Irrigation Canal at Pathway going to Balagbag Araw River | Brgy. Masiit | 996949.6 | 2017-12-01 |  | 86 | 857376.66 |  | On-Going | 139572.94
10 | Concrete box culvert & Drainage System at Sitio Lanzonesan | Brgy. Limao | 847016.82 | 2018-06-01 |  | 76.1811 | 645266.82 |  | On-Going | 201750
COVID 19 RELATED PROJECTS
11 | Procurement of Equipments, reagents and kits for COVID 19 testing | Calauan, Laguna | 500000 | 2021-03-01 |  | 55.3 | 276500 |  | On-Going | 223500
12 | Procurement of medicines & vitamins | Calauan, Laguna | 500000 | 2021-03-01 |  | 15.3883 | 76941.25 |  | On-Going | 423058.75
13 | Procurement of hospital / medical equipment and supplies | Calauan, Laguna | 500000 | 2021-03-01 |  | 32.8464 | 164232.2 |  | On-Going | 335767.8
14 | Expenses for the construction / lease/ rental of additional space / building to accommodate | Calauan, Laguna | 2500000 | 2021-03-01 |  | 5.28 | 132000 |  | On-Going | 2368000
CAPITAL OUTLAY (GENERAL FUND)
15 | Completion of Conference Hall / Dialysis Center |  | 4250996 | 2019-12-01 |  | 89.8625 | 3820053.2 |  | On-Going | 430942.8
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data of information contained in this
document.
| (sgd) | [5 empty] | (sgd)
| JOSE G. MEDEL | [5 empty] | BUENAFRIDO T. BERRIS
| Municipal Budget Officer I | [5 empty] | Local Chief Executive